## Sheet1
Group | Name | Lead | Team | Status | Start Date | End Date | Priority | Hours | Completion Date | Practice | Stakeholders | Allocation %
IP & Product | Defining pipeline for AI materials to collect | Savannah Ricard | Kay Bore, Savannah Ricard | Working | 2025-12-08 | 2026-04-17 | Low | 59.5 | 2026-03-25 | POP |  | 0
IP & Product | GenAI Talent Perspective | Savannah Ricard | Savannah Ricard, Kay Bore, Frank Anderson | Working | 2025-11-17 | 2026-06-05 | Medium | 36.75 | 2026-04-14 | POP |  | 0
IP & Product | Global study 2026 I BFF | Giuseppe Colombo | Giuseppe Colombo, Csilla Szalay, Frank Anderson | Working |  |  | Medium | 273 |  | TDA | Michael Grebe, Marc Roman Franke, Clemens Nopp | 0
IP & Product | AI Competitive Intelligence | Prashant Sharma, Rishabh Sharma | Prashant Sharma, Rishabh Sharma, Pranav Bhanot | Working |  |  | High | 112 | 2026-03-09 | TDA | Nicolas de Bellefonds, Liana Shalev | 0
IP & Product | Non agentic credentials deck | Prashant Sharma | Prashant Sharma | Working |  |  | High | 5.81 | 2026-03-09 | TDA | Nicolas de Bellefonds, Liana Shalev | 0
IP & Product | AI for Tech: Physical AI support | Marcus Pinnau, Eugene Hayden | Marcus Pinnau | Working |  |  | Medium | 10.5 |  | TDA | Daniel Kuepper | 0
IP & Product | AI for Tech: PDLC support | Chao Wei Lai | Chao Wei Lai, Frank Anderson, Csilla Szalay | Working |  |  | Medium | 220.15 | 2026-04-14 | TDA | Vikram Sivakumar, Joppe Bijlsma | 0
IP & Product | AI for Tech: Legacy Tech modernization | Michael Leyh, Mariana Chaverri, Frank Anderson | Michael Leyh, Mariana Chaverri | Working |  |  | Medium | 3.5 |  | TDA | Joppe Bijlsma, Julien Marx, Michael Fraser, Djon Kleine, Kevin Lucas | 0
IP & Product | Tech council proposals sanitization | Carmen Casas | Carmen Casas | Working | 2026-03-09 | 2026-05-06 | Low | 0 |  | POP/TDA | Nicolas de Bellefonds, Liana Shalev | 0
IP & Product | Sales AI |  | Evan Song | Working |  |  | Unset | 1310.05 |  |  |  | 0
IP & Product | Newsletter automation | Jun Wei Ee | Jun Wei Ee | Working | 2026-05-18 | 2026-06-05 | Unset | 0 |  |  |  | 0
IP & Product | AI platform | Giuseppe Colombo | Giuseppe Colombo, Jun Wei Ee | Working |  |  | Unset | 40.25 |  |  |  | 0
IP & Product | Token cost control perspective | Frank Anderson | Frank Anderson | Working | 2026-05-18 | 2026-06-05 | Unset | 14 |  |  |  | 0
Operations & Reporting | [Ongoing] BFF Helix support | Frank Anderson | Frank Anderson | Working | 2026-05-18 | 2026-06-05 | Unset | 33.25 |  | TDA |  | 0
Operations & Reporting | TDA/Feld Group Account Pilots | Savannah Ricard | Savannah Ricard | Working | 2025-11-17 | 2026-06-05 | Medium | 33.6 |  | POP |  | 0
Operations & Reporting | POPxTMT Support | Savannah Ricard | Savannah Ricard | Working | 2026-03-26 | 2026-04-17 | Deprioritized | 83.3 |  | POP |  | 0
Operations & Reporting | WWOM support | Florence Adida | Frank Anderson, Connor Currier, Veronika Bugaychuk | Working | 2025-10-27 | 2026-06-05 | Low | 88.9 | 2026-05-18 | POP |  | 0
Operations & Reporting | Open AI partnership support | Michael Leyh, Giuseppe Colombo | Giuseppe Colombo, Frank Anderson, Michael Leyh | Backlog |  |  | Deprioritized | 0.42 |  | POP/TDA | Dan Sacks | 0
Operations & Reporting | Recruiting | Chao Wei Lai, Giuseppe Colombo, Prashant Sharma, Eugene Hayden | Giuseppe Colombo, Chao Wei Lai, Prashant Sharma | Working | 2026-04-15 | 2026-05-06 | High | 50.75 | 2026-05-06 | POP/TDA | Hauke & Julie | 0
Operations & Reporting | Get togethers | Chao Wei Lai | Chao Wei Lai, Csilla Szalay | Working |  |  | Fastrack⚠️️ | 5.95 |  | TDA | Hauke & Julie | 0
Operations & Reporting | AI this week newsletter | Jun Wei Ee, Kay Bore, Evan Song, Margot Li, Carmen Casas, Eugene Hayden | Evan Song, Kay Bore, Jun Wei Ee | Working |  |  | Unset | 147.7 |  | POP/TDA | Djon Kleine | 0
Operations & Reporting | TDA.IG pipeline call | Marcus Pinnau, Michael Leyh | Marcus Pinnau | Working |  |  | Medium | 76.65 |  | TDA | Marc Andre Drillose | 0
Operations & Reporting | APAC AI Newsletter | Rishabh Sharma |  | Working |  |  | Unset | 4.9 |  | TDA |  | 0
Operations & Reporting | Office Hours rotations | Frank Anderson | Frank Anderson | Backlog | 2026-05-18 | 2026-06-05 | Low | 6.3 |  | POP |  | 0
Operations & Reporting | CDC activities | Giuseppe Colombo | Giuseppe Colombo | Backlog |  |  | Unset | 7 |  |  |  | 0
Marketing & Promotion | AI at Work 2026 | Florence Adida | Florence Adida, Jun Wei Ee | Working | 2026-03-26 | 2026-06-05 | Unset | 88.9 |  | POP |  | 0
Marketing & Promotion | BFF 2026 support | Frank Anderson | Frank Anderson, Florence Adida, Connor Currier | Working | 2026-02-09 | 2026-05-06 | Unset | 0 | 2026-05-06 | POP |  | 0
Marketing & Promotion | Edge WWOM preparation | Michael Leyh | Michael Leyh, Frank Anderson | Working |  |  | Unset | 144.2 |  | TDA | Nicole Monter | 0
Marketing & Promotion | Edge PDLC booth | Chao Wei Lai |  | Working |  |  | High | 38.5 |  | TDA | Vikram Sivakumar | 0
50% time | Connor |  | Connor Currier | Backlog | 2025-01-01 | 2030-01-01 | Unset | 4567.5 | 2025-07-15 | POP |  | 0